## Sheet1
Plan of Action and Milestone (POAM)
Xoreta Academy System
POAM ID | Creation Date | Security Control | Weakness Name | Weakness Description | Severity Level Critical /High/Moderate/Low | Cost ($) | Cost Justification | Point of Contact | Planned Start Date | Planned Finished Date | Schedule Completion Date | Milestone | Changes to Milestone | Actual Start Date | Actual Completion Date | Status
2 | 2023-11-04 | AC-6 | Least Privilege | It was discovered that some employees have elevated priviledges due to their accounts not being deactivated after being terminated. | High | 50 | one system admin will be designated to remediate, with a base income of $50/hr | Tobi | 2024-08-06 | 13/07/2024 | 13/07/2024 | System Admins will terminate the account of the employee | System admins sucessfully updated the Elevated privilege of the employee. | 2024-11-06 | 30/06/2024 | Completed